## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Bootstrap | Start round and clear round link placeholders missing from bootstrap page | Low | 1 | 7 | Use the planned debugging time in the iteration.
2 | 1 | Bootstrap | Failed to print correct number of bid.csv rows processed | High | 5
3 | 1 | Bootstrap | Course.php convertDateTime function var_dumps a bunch of datetime objects on json | Low | 1
4 | 2 | Authenticate | Error messages not in alphabetical order | Low | 1 | 46 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
5 | 2 | Bootstrap | Fatal error encountered: function name must be a string at line 10 | Critical | 10
6 | 2 | Bid Section | Bids below e$10 were accepted | High | 5
7 | 2 | Bid Section | Bids amount with more than 2 decimal places were accepted | High | 5
8 | 2 | Update Bid | Admin able to bid during inactive round | High | 5
9 | 2 | Update Bid | Error message should be 'section limit reached', not 'not own school course' | High | 5
10 | 2 | Delete Bid | Admin able to delete bid during inactive round | High | 5
11 | 2 | Drop Section | Admin unable to drop section despite valid inputs and active round | High | 5
12 | 2 | Drop Section | Error message should be 'round not active', not 'no such enrollment record' | High | 5
13
14 | 3 | Popular Place | Could not print K number of places | High | 5 | 20 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
15 | 3 | Popular Place | Null pointer exception raised when dealing with no data | High | 5
16 | 3 | Popular Place | Could not select "K" | High | 5
17 | 3 | Bootstrap | Could not delete from table when bootstrapping | High | 5
18 | 3 | Breakdown of Y&G | Retreive output table is not aligned properly | Low | 1 | 12 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
19 | 3 | Breakdown of Y&G | Null pointer exception raised when retreiving error message | High | 5
20 | 3 | Breakdown of Y&G | Unable to calculate percentage | Low | 1
21 | 3 | Breakdown of Y&G | Issue when retrieving total number of users, and cause null pointer exceptions | High | 5
22 | 3 | Login (User) | Failed login with wrong username and correct password | High | 5
23 | 3 | Login (Admin) | After successful login, login did not store name in session for display use at index_admin | Low | 1
24 | 3 | Login (User) | After successful login, login did not store name in session for display use at index | Low | 1
25 | 3 | Bootstrap | Crashes on upload with a "duplicate entry" database error | Critical | 10
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Bootstrap | Start round and clear round link placeholders missing from bootstrap page | Resolved | 2019-09-25 | 2019-09-25 | BWC & TS
2 | 1 | Bootstrap | Failed to print correct number of bid.csv rows processed | Resolved | 2019-09-25 | 2019-09-25 | BWC & TS
3 | 1 | Bootstrap | Course.php convertDateTime function var_dumps a bunch of datetime objects on json | Resolved | 2019-10-02 | 2019-10-02 | BWC & TS
4 | 2 | Authenticate | Error messages not in alphabetical order | Resolved | 2019-10-12 | 2019-10-13 | TS & LJY
5 | 2 | Bootstrap | Fatal error encountered: function name must be a string at line 10 | Resolved | 2019-10-12 | 2019-10-13 | TS & LJY
6 | 2 | Bid Section | Bids below e$10 were accepted | Resolved | 2019-10-12 | 2019-10-13 | TS & LJY
7 | 2 | Bid Section | Bids amount with more than 2 decimal places were accepted | Resolved | 2019-10-12 | 2019-10-13 | TS & LJY
8 | 2 | Update Bid | Admin able to bid during inactive round | Unresolved | 2019-10-12
9 | 2 | Update Bid | Error message should be 'section limit reached', not 'not own school course' | Unresolved | 2019-10-12
10 | 2 | Delete Bid | Admin able to delete bid during inactive round | Unresolved | 2019-10-12
11 | 2 | Drop Section | Admin unable to drop section despite valid inputs and active round | Unresolved | 2019-10-12
12 | 2 | Drop Section | Error message should be 'round not active', not 'no such enrollment record' | Unresolved | 2019-10-12
13 | 0
14 | 3 | Popular Place | Could not print K number of places | Resolved | 22/10/2017 | 22/10/2017 | H & J
15 | 3 | Popular Place | Null pointer exception raised when dealing with no data | Resolved | 22/10/2017 | 22/10/2017 | H & K
16 | 3 | Popular Place | Could not select "K" | Resolved | 22/10/2017 | 22/10/2017 | H & K
17 | 3 | Bootstrap | Could not delete from table when bootstrapping | Resolved | 22/10/2017
18 | 3 | Breakdown of Y&G | Retreive output table is not aligned properly | Resolved | 22/10/2017
19 | 3 | Breakdown of Y&G | Null pointer exception raised when retreiving error message | Resolved | 2017-10-21 | 2017-10-21 | J & P
20 | 3 | Breakdown of Y&G | Unable to calculate percentage | Resolved | 2017-10-21 | 2017-10-21 | J & P
21 | 3 | Breakdown of Y&G | Issue when retrieving total number of users, and cause null pointer exceptions | Resolved | 2017-10-21 | 2017-10-21 | J & P
22 | 3 | Login (User) | Failed login with wrong username and correct password
23 | 3 | Login (Admin) | After successful login, login did not store name in session for display use at index_admin
24 | 3 | Login (User) | After successful login, login did not store name in session for display use at index
25 | 3 | Bootstrap | Crashes on upload with a "duplicate entry" database error