## Week 5
Person | Question | Week: 16 Sep to 22 Sep
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Shermin | What did you do yesterday? | Not a working day | Pair Programme with Wei Chen (SQL scripts, StudentDAO, Student & ConnectionMgr files) | Not a working day | Brainstorm implementation of bid section function (use sql table to track bidding round) | Not a working day | Pair Programme with Wei Chen (Student and Admin index.php) | Pair Programme with Wei Chen (Student and Admin index.php)
| What will you do today? | Pair Programme with Wei Chen (SQL scripts and DAOs) | Not a working day | Brainstorm implementation of bid section function | Not a working day | Pair Programme with Wei Chen (Student and Admin index.php) | Pair Programme with Wei Chen (Student and Admin index.php) | Not a working day
| Do you have any obstacles? | No | No | Yes, keeping track of bidding round number | No | No | No | No
Beh Wei Chen | What did you do yesterday? | Not a working day | Pair Programme with Wei Chen (SQL scripts, StudentDAO, Student & ConnectionMgr files) | Not a working day | Brainstorm implementation of bid section function (use sql table to track bidding round) | Not a working day | Pair Programme with Shermin (Student and Admin index.php) | Pair Programme with Shermin (Student and Admin index.php)
| What will you work on today? | Pair Programme with Shermin (SQL scripts and DAOs) | Not a working day | Brainstorm implementation of bid section function | Not a working day | Pair Programme with Shermin (Student and Admin index.php) | Pair Programme with Shermin (Student and Admin index.php) | Not a working day
| Do you have any obstacles? | No | No | Yes, keeping track of bidding round number | No | No | No | No
Lim Jia Yu | What did you do yesterday? | Not a working day | Not a working day | Allocate files and functions to be programmed by the pairs | Not a working day | Plan which elements to display for each webpage | Not a working day | Identify critical path of schedule and update google sheet
| What will you work on today? | Not a working day | Allocate files and functions to be programmed by the pairs | Not a working day | Plan which elements to display for each webpage | Not a working day | Identify critical path of schedule and update google sheet | Not a working day
| Do you have any obstacles? | No | No | No | No | No | No | No
Wong Wei Ling | What did you do yesterday? | Not a working day | Plan Tuesday meeting/pair programming with Geralyn | Pair Programme with Geralyn (login.php and style.css) | Not a working day | Pair Programme with Geralyn (complete DAOs and classes) | Pair Programme with Geralyn (complete DAOs and classes) | Not a working day
| What will you work on today? | Plan Tuesday meeting/pair programming with Geralyn | Pair Programme with Geralyn (login.php and style.css) | Not a working day | Pair Programme with Geralyn (complete DAOs and classes) | Pair Programme with Geralyn (complete DAOs and classes) | Not a working day | Pair Programme with Geralyn (Work on Student.csv validation and Course.csv validation)
| Do you have any obstacles? | No | No | No | No | No | No | Uncertain as to how to validate date and time format
Geralyn Goo Soo Chi | What did you do yesterday? | Not a working day | Plan Tuesday meeting/pair programming with Wei Ling | Pair Programme with Wei Ling (login.php and style.css) | Not a working day | Pair Programme with Wei Ling (complete DAOs and classes) | Pair Programme with Wei Ling (complete DAOs and classes) | Not a working day
| What will you work on today? | Plan Tuesday meeting/pair programming with Wei Ling | Pair Programme with Wei Ling (login.php and style.css) | Not a working day | Pair Programme with Wei Ling (complete DAOs and classes) | Pair Programme with Wei Ling (complete DAOs and classes) | Not a working day | Pair Programme with Wei Ling (Work on Student.csv validation and Course.csv validation)
| Do you have any obstacles? | No | No | No | No | No | No | Uncertain as to how to validate date and time format

## Week 6
Person | Question | Week: 23 Sep to 29 Sep
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Shermin | What did you do yesterday? | Not a working day | Pair Programme with Wei Chen (section.csv and prerequisite.csv validation) | Not a working day | Pair Programme with Wei Chen (combine bootstrap function) | Not a working day | Pair Programme with Wei Chen (amend protect.php to separate student and admin logins) | Not a working day
| What will you do today? | Pair Programme with Wei Chen (section.csv and prerequisite.csv validation) | Not a working day | Pair Programme with Wei Chen (combine bootstrap function) | Not a working day | Pair Programme with Wei Chen (amend protect.php to separate student and admin logins) | Not a working day | PM Review Preparation
| Do you have any obstacles? | Whether there is an easy way to check for clash in class timetables | No | No | No | No | No | No
Beh Wei Chen | What did you do yesterday? | Not a working day | Pair Programme with Shermin (section.csv and prerequisite.csv validation) | Not a working day | Pair Programme with Shermin (combine bootstrap function) | Not a working day | Pair Programme with Shermin (amend protect.php to separate student and admin logins) | Not a working day
| What will you work on today? | Pair Programme with Shermin (section.csv and prerequisite.csv validation) | Not a working day | Pair Programme with Shermin (combine bootstrap function) | Not a working day | Pair Programme with Shermin (amend protect.php to separate student and admin logins) | Not a working day | PM Review Preparation
| Do you have any obstacles? | Whether there is an easy way to check for clash in class timetables | No | No | No | No | No | No
Lim Jia Yu | What did you do yesterday? | Not a working day | Come up with test cases for login function | Come up with test cases for login function | Not a working day | Come up with test cases for login function | Not a working day | Not a working day
| What will you work on today? | Come up with test cases for login function | Come up with test cases for login function | Not a working day | Come up with test cases for login function | Not a working day | Not a working day | PM Review Preparation
| Do you have any obstacles? | No | No | No | No | No | No | No
Wong Wei Ling | What did you do yesterday? | Pair Programme with Geralyn (Work on Student.csv validation and Course.csv validation) | Not a working day | Pair Programme with Geralyn (course_completed.csv and bid.csv validation) | Not a working day | Come up with test cases for bootstrap function | Come up with test cases for bootstrap function | Not a working day
| What will you work on today? | Not a working day | Pair Programme with Geralyn (course_completed.csv and bid.csv validation) | Not a working day | Come up with test cases for bootstrap function | Come up with test cases for bootstrap function | Not a working day | Pair Programme with Geralyn (authenticate and bootstrap Json checker)
| Do you have any obstacles? | No | No | No | No | No | No | No
Geralyn Goo Soo Chi | What did you do yesterday? | Pair Programme with Wei Ling (Work on Student.csv validation and Course.csv validation) | Not a working day | Pair Programme with Wei Ling (course_completed.csv and bid.csv validation) | Not a working day | Come up with test cases for bootstrap function | Come up with test cases for bootstrap function | Not a working day
| What will you work on today? | Not a working day | Pair Programme with Wei Ling (course_completed.csv and bid.csv validation) | Not a working day | Come up with test cases for bootstrap function | Come up with test cases for bootstrap function | Not a working day | Pair Programme with Wei Ling (authenticate and bootstrap Json checker)
| Do you have any obstacles? | No | No | No | No | No | No | No

## Week 7
Person | Question | Week: 30 Sep to 6 Oct
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Shermin | What did you do yesterday? | PM Review Preparation | Run bootstrap and login testcases | Prepare testcases and run it for login and bootstrap | Finish up bootstrap testcases + PM review preparations | PM Review | Team meeting for Iteration 2 (functions to complete, tasks to do and its allocation) | Drop bid function
| What will you do today? | Run bootstrap and login testcases | Prepare testcases and run it for login and bootstrap | Finish up bootstrap testcases + PM review preparations | PM Review | Team meeting for Iteration 2 (functions to complete, tasks to do and its allocation) | Drop bid function | Complete and combine place bid function
| Do you have any obstacles? | No | No | No | No | No | No | No
Beh Wei Chen | What did you do yesterday? | PM Review Preparation | Run bootstrap and login testcases | Prepare testcases and run it for login and bootstrap | Finish up bootstrap testcases + PM review preparations | PM Review | Team meeting for Iteration 2 (functions to complete, tasks to do and its allocation) | Work out Iteration 2 critical path
| What will you work on today? | Run bootstrap and login testcases | Prepare testcases and run it for login and bootstrap | Finish up bootstrap testcases + PM review preparations | PM Review | Team meeting for Iteration 2 (functions to complete, tasks to do and its allocation) | Work out Iteration 2 critical path | Not a working day
| Do you have any obstacles? | No | No | No | No | No | No | No
Lim Jia Yu | What did you do yesterday? | PM Review Preparation | PM Review Preparation | Bug Metrics preparation | PM review preparations | PM Review | Team meeting for Iteration 2 (functions to complete, tasks to do and its allocation) | Drop bid function
| What will you work on today? | PM Review Preparation | Bug Metrics preparation | PM review preparations | PM Review | Team meeting for Iteration 2 (functions to complete, tasks to do and its allocation) | Drop bid function | Complete and combine place bid function
| Do you have any obstacles? | No | No | No | No | No | No | No
Wong Wei Ling | What did you do yesterday? | Pair Programme with Geralyn (authenticate and bootstrap Json checker) | PM Review Preparation | Bug Metrics preparation | Deploy app + PM review preparations | PM Review | Team meeting for Iteration 2 (functions to complete, tasks to do and its allocation) | Place bid function (check active bidding round, invalid inputs and timetable clashes)
| What will you work on today? | PM Review Preparation | Bug Metrics preparation | Deploy app + PM review preparations | PM Review | Team meeting for Iteration 2 (functions to complete, tasks to do and its allocation) | Place bid function (check active bidding round, invalid inputs and timetable clashes) | Drop section function
| Do you have any obstacles? | No | No | Problem encountered when displaying pages | No | No | No | Success messages are not displayed in green
Geralyn Goo Soo Chi | What did you do yesterday? | Pair Programme with Wei Ling (authenticate and bootstrap Json checker) | PM Review Preparation | Bug Metrics preparation | Deploy app + PM review preparations | PM Review | Team meeting for Iteration 2 (functions to complete, tasks to do and its allocation) | Place bid function (check active bidding round, invalid inputs and timetable clashes)
| What will you work on today? | PM Review Preparation | Bug Metrics preparation | Deploy app + PM review preparations | PM Review | Team meeting for Iteration 2 (functions to complete, tasks to do and its allocation) | Place bid function (check active bidding round, invalid inputs and timetable clashes) | Drop section function
| Do you have any obstacles? | No | No | Problem encountered when displaying pages | No | No | No | Success messages are not displayed in green

## Week 8
Person | Question | Week: 7 Oct to 13 Oct
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Shermin | What did you do yesterday? | Complete and combine place bid function | Not a working day | Bid section and drop bid json checker | Bid section and drop bid json checker + testcases | Not a working day | Complete testcases | Complete testcases + start round function
| What will you do today? | Not a working day | Bid section and drop bid json checker | Bid section and drop bid json checker + testcases | Not a working day | Complete testcases | Complete testcases + start round function | Debug after running of testcase
| Do you have any obstacles? | No | No | No | No | No | No | No
Beh Wei Chen | What did you do yesterday? | Not a working day | Not a working day | Begin on testcases for the 3 new functions | Not a working day | Not a working day | Complete testcases | Complete testcases
| What will you work on today? | Not a working day | Begin on testcases for the 3 new functions | Not a working day | Not a working day | Complete testcases | Complete testcases | Prepare bug metrics
| Do you have any obstacles? | No | No | No | No | No | No | No
Lim Jia Yu | What did you do yesterday? | Complete and combine place bid function | Not a working day | Bid section and drop bid json checker | Continue with testcases for the 3 new functions | Not a working day | Complete testcases | Complete testcases + start round function
| What will you work on today? | Not a working day | Bid section and drop bid json checker | Bid section and drop bid json checker + testcases | Not a working day | Complete testcases | Complete testcases + start round function | Debug after running of testcase
| Do you have any obstacles? | No | No | No | No | No | No | No
Wong Wei Ling | What did you do yesterday? | Drop section function | Not a working day | Drop section json checker | Drop section json checker + testcases | Not a working day | Complete testcases | Complete testcases + clear round 1 function
| What will you work on today? | Not a working day | Drop section json checker | Drop section json checker + testcases | Not a working day | Complete testcases | Complete testcases + clear round 1 function | Clear round 2 function and combine it
| Do you have any obstacles? | No | No | No | No | No | No | No
Geralyn Goo Soo Chi | What did you do yesterday? | Drop section function | Not a working day | Drop section json checker | Drop section json checker + testcases | Not a working day | Complete testcases | Complete testcases + clear round 1 function
| What will you work on today? | Not a working day | Drop section json checker | Drop section json checker + testcases | Not a working day | Complete testcases | Complete testcases + clear round 1 function | Clear round 2 function and combine it
| Do you have any obstacles? | No | No | No | No | No | No | No

## Week 9
Person | Question | Week: 14 Oct to 20 Oct
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Shermin | What did you do yesterday? | Debug after running of testcase | Not a working day | Not a working day | Prepare app demo and progress update deliverables | App Demo & Progress Update | Plan for Iteration 3 tasks and its allocation | Not a working day
| What will you do today? | Not a working day | Not a working day | Prepare app demo and progress update deliverables | App Demo & Progress Update | Plan for Iteration 3 tasks and its allocation | Not a working day | Not a working day
| Do you have any obstacles? | No | No | No | No | No | No | No
Beh Wei Chen | What did you do yesterday? | Prepare bug metrics | Deploy app, test and debug | Not a working day | Prepare app demo and progress update deliverables | App Demo & Progress Update | Plan for Iteration 3 tasks and its allocation | Not a working day
| What will you work on today? | Deploy app, test and debug | Not a working day | Prepare app demo and progress update deliverables | App Demo & Progress Update | Plan for Iteration 3 tasks and its allocation | Not a working day | Clear round function (round 2)
| Do you have any obstacles? | No | No | No | No | No | No | No
Lim Jia Yu | What did you do yesterday? | Debug after running of testcase | Not a working day | Not a working day | Prepare app demo and progress update deliverables | App Demo & Progress Update | Plan for Iteration 3 tasks and its allocation | Not a working day
| What will you work on today? | Not a working day | Not a working day | Prepare app demo and progress update deliverables | App Demo & Progress Update | Plan for Iteration 3 tasks and its allocation | Not a working day | Clear round function (round 2)
| Do you have any obstacles? | No | No | No | No | No | No | No
Wong Wei Ling | What did you do yesterday? | Clear round 2 function and combine it | Not a working day | Not a working day | Prepare app demo and progress update deliverables | App Demo & Progress Update | Plan for Iteration 3 tasks and its allocation | Not a working day
| What will you work on today? | Not a working day | Not a working day | Prepare app demo and progress update deliverables | App Demo & Progress Update | Plan for Iteration 3 tasks and its allocation | Not a working day | Plan json checker functions' logic flow
| Do you have any obstacles? | No | No | No | No | No | No | No
Geralyn Goo Soo Chi | What did you do yesterday? | Clear round 2 function and combine it | Test deployed app and debug | Not a working day | Prepare app demo and progress update deliverables | App Demo & Progress Update | Plan for Iteration 3 tasks and its allocation | Not a working day
| What will you work on today? | Test deployed app and debug | Not a working day | Prepare app demo and progress update deliverables | App Demo & Progress Update | Plan for Iteration 3 tasks and its allocation | Not a working day | Plan json checker functions' logic flow
| Do you have any obstacles? | No | No | No | No | No | No | No

## Week 10
Person | Question | Week: 21 Oct to 27 Oct
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Shermin | What did you do yesterday? | Not a working day | Determine critical path for Iteration 3 | Not a working day | Not a working day
| What will you do today? | Determine critical path for Iteration 3 | Not a working day | Not a working day | Plan and allocate functions to the team to test
| Do you have any obstacles? | No | No | No | No
Beh Wei Chen | What did you do yesterday? | Clear round function (round 2) | Combine clear round function | Not a working day | Not a working day
| What will you work on today? | Combine clear round function | Not a working day | Not a working day | Dump table, user, bid, section, bid status json checker
| Do you have any obstacles? | No | No | No | No
Lim Jia Yu | What did you do yesterday? | Clear round function (round 2) | Combine clear round function | Not a working day | Not a working day
| What will you work on today? | Combine clear round function | Not a working day | Not a working day | Dump table, user, bid, section, bid status json checker
| Do you have any obstacles? | No | No | No | No
Wong Wei Ling | What did you do yesterday? | Plan json checker functions' logic flow | Plan json checker functions' logic flow | View bidding function | Not a working day
| What will you work on today? | Plan json checker functions' logic flow | View bidding function | Not a working day | Start round, stop round json checker
| Do you have any obstacles? | No | No | No | No
Geralyn Goo Soo Chi | What did you do yesterday? | Plan json checker functions' logic flow | Plan json checker functions' logic flow | View bidding function | Not a working day
| What will you work on today? | Plan json checker functions' logic flow | View bidding function | Not a working day | Start round, stop round json checker
| Do you have any obstacles? | No | No | No | No

## Week 11
Person | Question | Week: 28 Oct to 3 Nov
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Shermin | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Beh Wei Chen | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Lim Jia Yu | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Wong Wei Ling | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Geralyn Goo Soo Chi | What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Week 12
Person | Question | Week: 4 Nov to 10 Nov
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Shermin | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Beh Wei Chen | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Lim Jia Yu | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Wong Wei Ling | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Geralyn Goo Soo Chi | What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Week 13
Person | Question | Week: 11 Nov to 17 Nov
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Shermin | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Beh Wei Chen | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Lim Jia Yu | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Wong Wei Ling | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Geralyn Goo Soo Chi | What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Week 14
Person | Question | Week: 18 Nov to 24 Nov
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Shermin | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Beh Wei Chen | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Lim Jia Yu | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Wong Wei Ling | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Geralyn Goo Soo Chi | What did you do yesterday?
What will you work on today?
Do you have any obstacles?