## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Bootstrap | Start round and clear round link placeholders missing from bootstrap page | Low | 1 | 7 | Use the planned debugging time in the iteration.
2 | 1 | Bootstrap | Failed to print correct number of bid.csv rows processed | High | 5
3 | 1 | Bootstrap | Course.php convertDateTime function var_dumps a bunch of datetime objects on json | Low | 1
4 | 2 | Authenticate | Error messages not in alphabetical order | Low | 1 | 46 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
5 | 2 | Bootstrap | Fatal error encountered: function name must be a string at line 10 | Critical | 10
6 | 2 | Bid Section | Bids below e$10 were accepted | High | 5
7 | 2 | Bid Section | Bids amount with more than 2 decimal places were accepted | High | 5
8 | 2 | Update Bid | Admin able to bid during inactive round | High | 5
9 | 2 | Update Bid | Error message should be 'section limit reached', not 'not own school course' | High | 5
10 | 2 | Delete Bid | Admin able to delete bid during inactive round | High | 5
11 | 2 | Drop Section | Admin unable to drop section despite valid inputs and active round | High | 5
12 | 2 | Drop Section | Error message should be 'round not active', not 'no such enrollment record' | High | 5
13 | 3 | Student Index | Table cells for student timetable are printed completely off. | Low | 1 | 57 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
14 | 3 | Drop Bid/Section | During inactive rounds, courses are printed twice in the bidded and enrolled tables | Low | 1
15 | 3 | Start Round | Message status shows success when trying to start round during inactive round 2 | High | 5
16 | 3 | Dump Table | Incorrect output value for completed-course and prerequisite keys | High | 5
17 | 3 | Update Bid | Incorrect output when updating bid for previously enrolled course | High | 5
18 | 3 | Start Round | JSON output for round number is in string instead of integer | High | 5
19 | 3 | Drop Section | Error message: Undefined variable enrolment | Critical | 10
20 | 3 | Bid Status | JSON output for bids and enrolments are not sorted by bid, followed by userid | High | 5
21 | 3 | Bid Dump | Error message: Undefined offset 1 | Critical | 10
22 | 3 | Bid Status | Error message: Undefined index IS101 S1 | Critical | 10
23 | 4 | Round 1 Clearing Logic | Tie bids at clearing price, all should fail, instead, all succeded | High | 5 | 40 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
24 | 4 | Round 2 Minimum Price | After dropping bid, minimum price dropped instead of remaining constant | High | 5
25 | 4 | Clearing Logic | Minimum price amount for all courses were not shown | High | 5
26 | 4 | Dump Table | Dump table bids were ordered in ascending instead of descending order | High | 5
27 | 4 | Dump (Section) | Successful student enrolments were displayed incorrectly | High | 5
28 | 4 | Bootstrap | Error messages not sorted by file followed by line number | High | 5
29 | 4 | Dump (Bid) | result' field displayed incorrectly (?) | High | 5
30 | 4 | Clearing Logic | Error message: Undefined offset 0 in process_round_logic | High | 5

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Bootstrap | Start round and clear round link placeholders missing from bootstrap page | Resolved | 2019-09-25 | 2019-09-25 | BWC & TS
2 | 1 | Bootstrap | Failed to print correct number of bid.csv rows processed | Resolved | 2019-09-25 | 2019-09-25 | BWC & TS
3 | 1 | Bootstrap | Course.php convertDateTime function var_dumps a bunch of datetime objects on json | Resolved | 2019-10-02 | 2019-10-02 | BWC & TS
4 | 2 | Authenticate | Error messages not in alphabetical order | Resolved | 2019-10-12 | 2019-10-13 | TS & LJY
5 | 2 | Bootstrap | Fatal error encountered: function name must be a string at line 10 | Resolved | 2019-10-12 | 2019-10-13 | TS & LJY
6 | 2 | Bid Section | Bids below e$10 were accepted | Resolved | 2019-10-12 | 2019-10-13 | TS & LJY
7 | 2 | Bid Section | Bids amount with more than 2 decimal places were accepted | Resolved | 2019-10-12 | 2019-10-13 | TS & LJY
8 | 2 | Update Bid | Admin able to bid during inactive round | Resolved | 2019-10-12 | 2019-10-28 | BWC & LJY
9 | 2 | Update Bid | Error message should be 'section limit reached', not 'not own school course' | Resolved | 2019-10-12 | 2019-10-28 | BWC & LJY
10 | 2 | Delete Bid | Admin able to delete bid during inactive round | Resolved | 2019-10-12 | 2019-10-28 | BWC & LJY
11 | 2 | Drop Section | Admin unable to drop section despite valid inputs and active round | Resolved | 2019-10-12 | 2019-10-28 | BWC & LJY
12 | 2 | Drop Section | Error message should be 'round not active', not 'no such enrollment record' | Resolved | 2019-10-12 | 2019-10-28 | BWC & LJY
13 | 3 | Student Index | Table cells for student timetable are printed completely off. | Resolved | 2019-10-28 | 2019-10-28 | BWC & LJY
14 | 3 | Dump Table | Incorrect output value for completed-course and prerequisite keys | Resolved | 2019-10-28 | 2019-10-28 | BWC & LJY
15 | 3 | Start Round | Message status shows success when trying to start round during inactive round 2 | Resolved | 2019-10-28 | 2019-10-28 | BWC & LJY
16 | 3 | Dump Table | Incorrect output value for completed-course and prerequisite keys | Resolved | 2019-10-28 | 2019-10-28 | BWC & LJY
17 | 3 | Update Bid | Incorrect output when updating bid for previously enrolled course | Resolved | 2019-10-28 | 2019-10-28 | BWC & LJY
18 | 3 | Start Round | JSON output for round number is in string instead of integer | Resolved | 2019-10-28 | 2019-10-28 | BWC & LJY
19 | 3 | Bid Dump | Error message: Undefined offset 1 | Resolved | 2019-10-28 | 2019-10-28 | BWC & LJY
20 | 3 | Bid Status | JSON output for bids and enrolments are not sorted by bid, followed by userid | Resolved | 2019-10-28 | 2019-10-28 | BWC & LJY
21 | 3 | Bid Dump | Error message: Undefined offset 1 | Resolved | 2019-10-28 | 2019-10-28 | BWC & LJY
22 | 3 | Bid Status | Error message: Undefined index IS101 S1 | Resolved | 2019-10-28 | 2019-10-28 | BWC & LJY
23 | 4 | Round 1 Clearing Logic | Tie bids at clearing price, all should fail, instead, all succeded | Resolved | 2019-10-31 | 2019-10-31
24 | 4 | Round 2 Minimum Price | After dropping bid, minimum price dropped instead of remaining constant | Resolved | 2019-10-31 | 2019-10-31
25 | 4 | Clearing Logic | Minimum price amount for all courses were not shown | Resolved | 2019-10-31 | 2019-10-31
26 | 4 | Dump Table | Dump table bids were ordered in ascending instead of descending order | Resolved | 2019-11-09 | 2019-11-09
27 | 4 | Dump (Section) | Successful student enrolments were displayed incorrectly | Resolved | 2019-11-09 | 2019-11-09
28 | 4 | Bootstrap | Error messages not sorted by file followed by line number | Resolved | 2019-11-09 | 2019-11-09
29 | 4 | Dump (Bid) | result' field displayed incorrectly (?) | Resolved | 2019-11-09 | 2019-11-09
30 | 4 | Clearing Logic | Error message: Undefined offset 0 in process_round_logic | Resolved | 2019-11-09 | 2019-11-09