## Iter 1-Manual-Login Bootstrap
S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Actual Results | Pass/Fail
1 | Login (Student) | Validate that student with correct credentials can login | Username: ben.ng.2009 Password: qwerty129 | Put username into username input field and password into password input field. Submit | Login succeed. Home page displayed | Login succeed. Home page displayed | Pass
2 | Login (Student) | Validate that student with incorrect password cannot login | Username: ben.ng.2009 Password: qwerty130 | Put username into username input field and password into password input field. Submit | Login failed. Error message shown. | Login failed. Error message shown. | Pass
3 | Login (Student) | Validate that student with incorrect username cannot login | Username: ben.nng.2009 Password: qwerty129 | Put username into username input field and password into password input field. Submit | Login failed. Error message shown. | Login failed. Error message shown. | Pass
4 | Login (Student) | Validate that student with incorrect username and password cannot login | Username: benn.ng.2009 Password: qwerty130 | Put username into username input field and password into password input field. Submit | Login failed. Error message shown. | Login failed. Error message shown. | Pass
5 | Login (User) | Validate that inexistent student record cannot login | Username: edward.tan.2009 Password: qwerty100 | Put username into username input field and password into password input field. Submit | Login failed. Error message shown. | Login failed. Error message shown. | Pass | Do we want this? Or just remove?
6 | Login (Admin) | Validate that admin with correct credentials can login | Username: admin Password: skulked4154]campsite | Put username into username input field and password into password input field. Submit | Login failed. Error message shown. | Login failed. Error message shown. | Pass
7 | Login (Admin) | Validate that admin with incorrect password cannot login | Username: admin1 Password: skulked4154]campsite | Put username into username input field and password into password input field. Submit | Login failed. Error message shown. | Login failed. Error message shown. | Pass
8 | Login (Admin) | Validate that admin with incorrect username cannot login | Username: admin Password: qwerty | Put username into username input field and password into password input field. Submit | Login failed. Error message shown. | Login failed. Error message shown. | Pass
9 | Login (Admin) | Validate that admin with incorrect username and password cannot login | Username: admins Password: hello | Put username into username input field and password into password input field. Submit | Login failed. Error message shown. | Login failed. Error message shown. | Pass
10 | Bootstrap | Validate successful bootstrap | 005-bootstrap.zip | Click 'Choose File' and upload the required zip file. Submit | { "status": "success", "num-record-loaded": [ {"bid.csv": 11}, {"course.csv": 24}, {"course_completed.csv": 4}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 15} ] } | { "status": "success", "num-record-loaded": [ {"bid.csv": 11}, {"course.csv": 24}, {"course_completed.csv": 4}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 15} ] } | Pass
11 | Bootstrap | Validate unsuccessful authentication due to missing csv file (bid.csv) | 006-bootstrap.zip | Click 'Choose File' and upload the required zip file. Submit | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 0}, {"course_completed.csv": 0}, {"prerequisite.csv": 0}, {"section.csv": 0}, {"student.csv": 0} ], "error": [ "input files not found" ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 0}, {"course_completed.csv": 0}, {"prerequisite.csv": 0}, {"section.csv": 0}, {"student.csv": 0} ], "error": [ "input files not found" ] } | Pass
12 | Bootstrap | Validate unsuccessful bootstrap due to blank bid fields | 007-bootstrap.zip | Click 'Choose File' and upload the required zip file. Submit | { "status": "error", "num-record-loaded": [ {"bid.csv": 9}, {"course.csv": 24}, {"course_completed.csv": 4}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 15} ], "error": [ { "file": "bid.csv", "line": 6, "message": [ "blank amount", "blank section" ] }, { "file": "bid.csv", "line": 11, "message": [ "blank userid", "blank code" ] } ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 9}, {"course.csv": 24}, {"course_completed.csv": 4}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 15} ], "error": [ { "file": "bid.csv", "line": 6, "message": [ "blank amount", "blank section" ] }, { "file": "bid.csv", "line": 11, "message": [ "blank userid", "blank code" ] } ] } | Pass
13 | Bootstrap | Validate unsuccessful bootstrap due to blank student fields | 008-bootstrap.zip | Click 'Choose File' and upload the required zip file. Submit | { "status": "error", "num-record-loaded": [ {"bid.csv": 10}, {"course.csv": 24}, {"course_completed.csv": 3}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 13} ], "error": [ { "file": "student.csv", "line": 8, "message": [ "blank userid", "blank password" ] }, { "file": "student.csv", "line": 9, "message": [ "blank name", "blank school" ] } ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 10}, {"course.csv": 24}, {"course_completed.csv": 3}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 13} ], "error": [ { "file": "student.csv", "line": 8, "message": [ "blank userid", "blank password" ] }, { "file": "student.csv", "line": 9, "message": [ "blank name", "blank school" ] } ] } | Pass
14 | Bootstrap | Validate unsuccessful bootstrap due to course-specific errors | 009-bootstrap.zip | Click 'Choose File' and upload the required zip file. Submit | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 22}, {"course_completed.csv": 0}, {"prerequisite.csv": 0}, {"section.csv": 0}, {"student.csv": 0} ], "error": [ { "file": "course.csv", "line": 2, "message": [ "invalid exam date", "invalid exam start", "invalid exam end" ] }, { "file": "course.csv", "line": 3, "message": [ "invalid exam date", "invalid exam end", "invalid title", "invalid description" ] } ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 22}, {"course_completed.csv": 0}, {"prerequisite.csv": 0}, {"section.csv": 0}, {"student.csv": 0} ], "error": [ { "file": "course.csv", "line": 2, "message": [ "invalid exam date", "invalid exam start", "invalid exam end" ] }, { "file": "course.csv", "line": 3, "message": [ "invalid exam date", "invalid exam end", "invalid title", "invalid description" ] } ] } | Pass
15 | Bootstrap | Validate unsuccessful bootstrap due to section-specific errors | 010-bootstrap.zip | Click 'Choose File' and upload the required zip file. Submit | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 23}, {"course_completed.csv": 0}, {"prerequisite.csv": 0}, {"section.csv": 32}, {"student.csv": 0} ], "error": [ { "file": "section.csv", "line": 2, "message": [ "invalid course", "invalid day", "invalid start", "invalid end", "invalid instructor", "invalid venue", "invalid size" ] }, { "file": "section.csv", "line": 3, "message": [ "invalid course", "invalid day", "invalid start", "invalid end", "invalid size" ] }, { "file": "section.csv", "line": 4, "message": [ "invalid section", "invalid day" ] } ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 23}, {"course_completed.csv": 0}, {"prerequisite.csv": 0}, {"section.csv": 32}, {"student.csv": 0} ], "error": [ { "file": "section.csv", "line": 2, "message": [ "invalid course", "invalid day", "invalid start", "invalid end", "invalid instructor", "invalid venue", "invalid size" ] }, { "file": "section.csv", "line": 3, "message": [ "invalid course", "invalid day", "invalid start", "invalid end", "invalid size" ] }, { "file": "section.csv", "line": 4, "message": [ "invalid section", "invalid day" ] } ] } | Pass
16 | Bootstrap | Validate unsuccessful bootstrap due to student-specific errors | 011-bootstrap.zip | Click 'Choose File' and upload the required zip file. Submit | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 24}, {"course_completed.csv": 0}, {"prerequisite.csv": 0}, {"section.csv": 35}, {"student.csv": 24} ], "error": [ { "file": "student.csv", "line": 2, "message": [ "invalid userid", "invalid e-dollar", "invalid password", "invalid name" ] }, { "file": "student.csv", "line": 4, "message": [ "duplicate userid", "invalid e-dollar" ] } ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 24}, {"course_completed.csv": 0}, {"prerequisite.csv": 0}, {"section.csv": 35}, {"student.csv": 24} ], "error": [ { "file": "student.csv", "line": 2, "message": [ "invalid userid", "invalid e-dollar", "invalid password", "invalid name" ] }, { "file": "student.csv", "line": 4, "message": [ "duplicate userid", "invalid e-dollar" ] } ] } | Pass
17 | Bootstrap | Validate unsuccessful bootstrap due to prerequisite-specific errors | 012-bootstrap.zip | Click 'Choose File' and upload the required zip file. Submit | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 24}, {"course_completed.csv": 0}, {"prerequisite.csv": 7}, {"section.csv": 35}, {"student.csv": 26} ], "error": [ { "file": "prerequisite.csv", "line": 2, "message": [ "invalid course", "invalid prerequisite" ] } ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 24}, {"course_completed.csv": 0}, {"prerequisite.csv": 7}, {"section.csv": 35}, {"student.csv": 26} ], "error": [ { "file": "prerequisite.csv", "line": 2, "message": [ "invalid course", "invalid prerequisite" ] } ] } | Pass
18 | Bootstrap | Validate unsuccessful bootstrap due to course_completed-specific errors | 013-bootstrap.zip | Click 'Choose File' and upload the required zip file. Submit | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 24}, {"course_completed.csv": 1}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 26} ], "error": [ { "file": "course_completed.csv", "line": 2, "message": [ "invalid userid", "invalid course" ] }, { "file": "course_completed.csv", "line": 3, "message": [ "invalid course completed" ] } ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 24}, {"course_completed.csv": 1}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 26} ], "error": [ { "file": "course_completed.csv", "line": 2, "message": [ "invalid userid", "invalid course" ] }, { "file": "course_completed.csv", "line": 3, "message": [ "invalid course completed" ] } ] } | Pass
19 | Bootstrap | Validate unsuccessful bootstrap due to bid-specific errors (field validation) | 014-bootstrap.zip | Click 'Choose File' and upload the required zip file. Submit | { "status": "error", "num-record-loaded": [ {"bid.csv": 8}, {"course.csv": 24}, {"course_completed.csv": 4}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 26} ], "error": [ { "file": "bid.csv", "line": 2, "message": [ "invalid userid", "invalid amount", "invalid course" ] }, { "file": "bid.csv", "line": 3, "message": [ "invalid amount", "invalid section" ] }, { "file": "bid.csv", "line": 4, "message": [ "invalid amount" ] } ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 8}, {"course.csv": 24}, {"course_completed.csv": 4}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 26} ], "error": [ { "file": "bid.csv", "line": 2, "message": [ "invalid userid", "invalid amount", "invalid course" ] }, { "file": "bid.csv", "line": 3, "message": [ "invalid amount", "invalid section" ] }, { "file": "bid.csv", "line": 4, "message": [ "invalid amount" ] } ] } | Pass
20 | Bootstrap | Validate unsuccessful bootstrap due to bid-specific errors (logic validation) | 015-bootstrap.zip | Click 'Choose File' and upload the required zip file. Submit | { "status": "error", "num-record-loaded": [ {"bid.csv": 7}, {"course.csv": 27}, {"course_completed.csv": 7}, {"prerequisite.csv": 8}, {"section.csv": 38}, {"student.csv": 26} ], "error": [ { "file": "bid.csv", "line": 4, "message": [ "class timetable clash", "exam timetable clash", "incomplete prerequisites", "not enough e-dollar" ] }, { "file": "bid.csv", "line": 10, "message": [ "not own school course", "course completed", "section limit reached" ] }, { "file": "bid.csv", "line": 11, "message": [ "class timetable clash", "exam timetable clash", "section limit reached" ] } ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 7}, {"course.csv": 27}, {"course_completed.csv": 7}, {"prerequisite.csv": 8}, {"section.csv": 38}, {"student.csv": 26} ], "error": [ { "file": "bid.csv", "line": 4, "message": [ "class timetable clash", "exam timetable clash", "incomplete prerequisites", "not enough e-dollar" ] }, { "file": "bid.csv", "line": 10, "message": [ "not own school course", "course completed", "section limit reached" ] }, { "file": "bid.csv", "line": 11, "message": [ "class timetable clash", "exam timetable clash", "section limit reached" ] } ] } | Pass

## Iter 1–JSON–Auth Bootstrap
S/N | Description | Test Inputs | Expected Results | Actual Results | Pass/Fail
001-authenticate | Validate successful authentication | Username: admin Password: skulked4154]campsite | { "status": "success", "token": "eyJ0eXAiOiJKV1QiLCJhbGciOiJIUzI1NiJ9.eyJ1c2VybmFtZSI6ImFkbWluIiwiZGF0ZXRpbWUiOiIyMDE5LTEwLTAxIDE0OjQ2OjQ4In0.D3Hxxr9aB4YLP1dOpp0xuUedjc5d_l0pI9Y-20OE0G8" } | { "status": "success", "token": "eyJ0eXAiOiJKV1QiLCJhbGciOiJIUzI1NiJ9.eyJ1c2VybmFtZSI6ImFkbWluIiwiZGF0ZXRpbWUiOiIyMDE5LTEwLTAxIDE0OjQ2OjQ4In0.D3Hxxr9aB4YLP1dOpp0xuUedjc5d_l0pI9Y-20OE0G8" } | Pass
002-authenticate | Validate unsuccessful authentication due to incorrect username | Username: admin1 Password: skulked4154]campsite | { "status": "error", "messages": [ "invalid username\/password" ] } | { "status": "error", "messages": [ "invalid username\/password" ] } | Pass
003-authenticate | Validate unsuccessful authentication due to incorrect password | Username: admin Password: qwerty | { "status": "error", "messages": [ "invalid username\/password" ] } | { "status": "error", "messages": [ "invalid username\/password" ] } | Pass
004-authenticate | Validate unsuccessful authentication due to incorrect username and password | Username: admins Password: hello | { "status": "error", "messages": [ "invalid username\/password" ] } | { "status": "error", "messages": [ "invalid username\/password" ] } | Pass
005-bootstrap | Validate successful bootstrap | 005-bootstrap.zip | { "status": "success", "num-record-loaded": [ {"bid.csv": 11}, {"course.csv": 24}, {"course_completed.csv": 4}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 15} ] } | { "status": "success", "num-record-loaded": [ {"bid.csv": 11}, {"course.csv": 24}, {"course_completed.csv": 4}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 15} ] } | Pass
006-bootstrap | Validate unsuccessful authentication due to missing csv file (bid.csv) | 006-bootstrap.zip | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 0}, {"course_completed.csv": 0}, {"prerequisite.csv": 0}, {"section.csv": 0}, {"student.csv": 0} ], "error": [ "input files not found" ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 0}, {"course_completed.csv": 0}, {"prerequisite.csv": 0}, {"section.csv": 0}, {"student.csv": 0} ], "error": [ "input files not found" ] } | Pass
007-bootstrap | Validate unsuccessful bootstrap due to blank bid fields | 007-bootstrap.zip | { "status": "error", "num-record-loaded": [ {"bid.csv": 9}, {"course.csv": 24}, {"course_completed.csv": 4}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 15} ], "error": [ { "file": "bid.csv", "line": 6, "message": [ "blank amount", "blank section" ] }, { "file": "bid.csv", "line": 11, "message": [ "blank userid", "blank code" ] } ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 9}, {"course.csv": 24}, {"course_completed.csv": 4}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 15} ], "error": [ { "file": "bid.csv", "line": 6, "message": [ "blank amount", "blank section" ] }, { "file": "bid.csv", "line": 11, "message": [ "blank userid", "blank code" ] } ] } | Pass
008-bootstrap | Validate unsuccessful bootstrap due to blank student fields | 008-bootstrap.zip | { "status": "error", "num-record-loaded": [ {"bid.csv": 10}, {"course.csv": 24}, {"course_completed.csv": 3}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 13} ], "error": [ { "file": "student.csv", "line": 8, "message": [ "blank userid", "blank password" ] }, { "file": "student.csv", "line": 9, "message": [ "blank name", "blank school" ] } ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 10}, {"course.csv": 24}, {"course_completed.csv": 3}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 13} ], "error": [ { "file": "student.csv", "line": 8, "message": [ "blank userid", "blank password" ] }, { "file": "student.csv", "line": 9, "message": [ "blank name", "blank school" ] } ] } | Pass
009-bootstrap | Validate unsuccessful bootstrap due to course-specific errors | 009-bootstrap.zip | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 22}, {"course_completed.csv": 0}, {"prerequisite.csv": 0}, {"section.csv": 0}, {"student.csv": 0} ], "error": [ { "file": "course.csv", "line": 2, "message": [ "invalid exam date", "invalid exam start", "invalid exam end" ] }, { "file": "course.csv", "line": 3, "message": [ "invalid exam date", "invalid exam end", "invalid title", "invalid description" ] } ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 22}, {"course_completed.csv": 0}, {"prerequisite.csv": 0}, {"section.csv": 0}, {"student.csv": 0} ], "error": [ { "file": "course.csv", "line": 2, "message": [ "invalid exam date", "invalid exam start", "invalid exam end" ] }, { "file": "course.csv", "line": 3, "message": [ "invalid exam date", "invalid exam end", "invalid title", "invalid description" ] } ] } | Pass
010-bootstrap | Validate unsuccessful bootstrap due to section-specific errors | 010-bootstrap.zip | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 23}, {"course_completed.csv": 0}, {"prerequisite.csv": 0}, {"section.csv": 32}, {"student.csv": 0} ], "error": [ { "file": "section.csv", "line": 2, "message": [ "invalid course", "invalid day", "invalid start", "invalid end", "invalid instructor", "invalid venue", "invalid size" ] }, { "file": "section.csv", "line": 3, "message": [ "invalid course", "invalid day", "invalid start", "invalid end", "invalid size" ] }, { "file": "section.csv", "line": 4, "message": [ "invalid section", "invalid day" ] } ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 23}, {"course_completed.csv": 0}, {"prerequisite.csv": 0}, {"section.csv": 32}, {"student.csv": 0} ], "error": [ { "file": "section.csv", "line": 2, "message": [ "invalid course", "invalid day", "invalid start", "invalid end", "invalid instructor", "invalid venue", "invalid size" ] }, { "file": "section.csv", "line": 3, "message": [ "invalid course", "invalid day", "invalid start", "invalid end", "invalid size" ] }, { "file": "section.csv", "line": 4, "message": [ "invalid section", "invalid day" ] } ] } | Pass
011-bootstrap | Validate unsuccessful bootstrap due to student-specific errors | 011-bootstrap.zip | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 24}, {"course_completed.csv": 0}, {"prerequisite.csv": 0}, {"section.csv": 35}, {"student.csv": 24} ], "error": [ { "file": "student.csv", "line": 2, "message": [ "invalid userid", "invalid e-dollar", "invalid password", "invalid name" ] }, { "file": "student.csv", "line": 4, "message": [ "duplicate userid", "invalid e-dollar" ] } ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 24}, {"course_completed.csv": 0}, {"prerequisite.csv": 0}, {"section.csv": 35}, {"student.csv": 24} ], "error": [ { "file": "student.csv", "line": 2, "message": [ "invalid userid", "invalid e-dollar", "invalid password", "invalid name" ] }, { "file": "student.csv", "line": 4, "message": [ "duplicate userid", "invalid e-dollar" ] } ] } | Pass
012-bootstrap | Validate unsuccessful bootstrap due to prerequisite-specific errors | 012-bootstrap.zip | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 24}, {"course_completed.csv": 0}, {"prerequisite.csv": 7}, {"section.csv": 35}, {"student.csv": 26} ], "error": [ { "file": "prerequisite.csv", "line": 2, "message": [ "invalid course", "invalid prerequisite" ] } ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 24}, {"course_completed.csv": 0}, {"prerequisite.csv": 7}, {"section.csv": 35}, {"student.csv": 26} ], "error": [ { "file": "prerequisite.csv", "line": 2, "message": [ "invalid course", "invalid prerequisite" ] } ] } | Pass
013-bootstrap | Validate unsuccessful bootstrap due to course_completed-specific errors | 013-bootstrap.zip | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 24}, {"course_completed.csv": 1}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 26} ], "error": [ { "file": "course_completed.csv", "line": 2, "message": [ "invalid userid", "invalid course" ] }, { "file": "course_completed.csv", "line": 3, "message": [ "invalid course completed" ] } ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 0}, {"course.csv": 24}, {"course_completed.csv": 1}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 26} ], "error": [ { "file": "course_completed.csv", "line": 2, "message": [ "invalid userid", "invalid course" ] }, { "file": "course_completed.csv", "line": 3, "message": [ "invalid course completed" ] } ] } | Pass
014-bootstrap | Validate unsuccessful bootstrap due to bid-specific errors (field validation) | 014-bootstrap.zip | { "status": "error", "num-record-loaded": [ {"bid.csv": 8}, {"course.csv": 24}, {"course_completed.csv": 4}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 26} ], "error": [ { "file": "bid.csv", "line": 2, "message": [ "invalid userid", "invalid amount", "invalid course" ] }, { "file": "bid.csv", "line": 3, "message": [ "invalid amount", "invalid section" ] }, { "file": "bid.csv", "line": 4, "message": [ "invalid amount" ] } ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 8}, {"course.csv": 24}, {"course_completed.csv": 4}, {"prerequisite.csv": 8}, {"section.csv": 35}, {"student.csv": 26} ], "error": [ { "file": "bid.csv", "line": 2, "message": [ "invalid userid", "invalid amount", "invalid course" ] }, { "file": "bid.csv", "line": 3, "message": [ "invalid amount", "invalid section" ] }, { "file": "bid.csv", "line": 4, "message": [ "invalid amount" ] } ] } | Pass
015-bootstrap | Validate unsuccessful bootstrap due to bid-specific errors (logic validation) | 015-bootstrap.zip | { "status": "error", "num-record-loaded": [ {"bid.csv": 7}, {"course.csv": 27}, {"course_completed.csv": 7}, {"prerequisite.csv": 8}, {"section.csv": 38}, {"student.csv": 26} ], "error": [ { "file": "bid.csv", "line": 4, "message": [ "class timetable clash", "exam timetable clash", "incomplete prerequisites", "not enough e-dollar" ] }, { "file": "bid.csv", "line": 10, "message": [ "not own school course", "course completed", "section limit reached" ] }, { "file": "bid.csv", "line": 11, "message": [ "class timetable clash", "exam timetable clash", "section limit reached" ] } ] } | { "status": "error", "num-record-loaded": [ {"bid.csv": 7}, {"course.csv": 27}, {"course_completed.csv": 7}, {"prerequisite.csv": 8}, {"section.csv": 38}, {"student.csv": 26} ], "error": [ { "file": "bid.csv", "line": 4, "message": [ "class timetable clash", "exam timetable clash", "incomplete prerequisites", "not enough e-dollar" ] }, { "file": "bid.csv", "line": 10, "message": [ "not own school course", "course completed", "section limit reached" ] }, { "file": "bid.csv", "line": 11, "message": [ "class timetable clash", "exam timetable clash", "section limit reached" ] } ] } | Pass

## Iter2-Manual-PlceBidDrpBidSect
S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Actual Results | Pass/Fail
1 | 016-bid | Validate that student is able to bid for any section with enough e$, class & timetables do not clash, and has fulfilled the necessary pre-requisite courses during an active bidding round. | Home Page Username: ben.ng.2009 Password: qwerty129 Bid Section Page Course ID: IS100 Section: S1 Bid (e$): 11 | Change to round 1. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field, section into section input field and bid amount into bid(e$) input field. Submit. | Bid successful. User is redirected back to page with success message.
2 | 017-bid | Validate that student is unable to bid during non-active bidding rounds. | Home Page Username: ben.ng.2009 Password: qwerty129 Bid Section Page Course ID: IS100 Section: S1 Bid (e$): 11 | Change to inactive bidding round. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field, section into section input field and bid amount into bid(e$) input field. Submit. | Bid unsuccessful. Error message shown.
3 | 018-bid | Validate that student is unable to bid for courses out of his/her school if it is bidding round 1. | Home Page Username: parker.ng.2009 Password: qwerty143 Bid Section Page Course ID: MGMT001 Section: S1 Bid (e$): 11 | Change to bidding round 1. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field, section into section input field and bid amount into bid(e$) input field. Submit. | Bid unsuccessful. Error message shown.
| 019-bid | Validate that student is unable to bid for courses if his/her bid is not a positive number>= e$10.00 | Home Page Username: ben.ng.2009 Password: qwerty129 Bid Section Page Course ID: IS100 Section: S1 Bid (e$): 9.00 | Change to bidding round 1. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field, section into section input field and bid amount into bid(e$) input field. Submit. | Bid unsuccessful. Error message shown.
| 019-bid | Validate that student is unable to bid for courses if his/her bid is more than 2 decimal places | Home Page Username: ben.ng.2009 Password: qwerty129 Bid Section Page Course ID: IS100 Section: S1 Bid (e$): 10.003 | Change to bidding round 1. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field, section into section input field and bid amount into bid(e$) input field. Submit. | Bid unsuccessful. Error message shown.
4 | 019-bid | Validate that student is unable to bid for courses if he/she has insufficient e$. | Home Page Username: ben.ng.2009 Password: qwerty129 Bid Section Page Course ID: IS100 Section: S1 Bid (e$): 201 | Change to bidding round 1. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field, section into section input field and bid amount into bid(e$) input field. Submit. | Bid unsuccessful. Error message shown.
5 | 020-bid | Validate that student is unable to bid for courses if he/she has already bidded for more than 5 sections. | Home Page Username: ben.ng.2009 Password: qwerty129 Bid Section Page Course ID: IS100 Section: S1 Bid (e$): 50 | Change to bidding round 1. Put username into username input field and password into password input field. Submit. Bid for 5 sections. Put course ID into course ID input field, section into section input field and bid amount into bid(e$) input field. Submit. | Bid unsuccessful. Error message shown.
6 | 021-bid | Validate that student is unable to bid if he/she has bidded for another section under the same course. | Home Page Username: ben.ng.2009 Password: qwerty129 Bid Section Page Course ID: IS100 Section: S2 Bid (e$): 50 | Change to bidding round 1. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field, section into section input field and bid amount into bid(e$) input field. Submit. Repeat above step. | Bid unsuccessful. Error message shown.
7 | 022-bid | Validate that student is unable to bid if there is a clash in class timetables. | Home Page Username: ben.ng.2009 Password: qwerty129 Bid Section Page Course ID: IS100 Section: S1 Bid (e$): 50 | Change to bidding round 1. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field, section into section input field and bid amount into bid(e$) input field. Submit. Submit another bid, with course ID: IS106, Section: S1, Bid(e$): 50 | Bid unsuccessful. Error message shown.
8 | 023-bid | Validate that student is unable to bid if he/she has not completed pre-requisite courses. | Home Page Username: calvin.ng.2009 Password: qwerty130 Bid Section Page Course ID: IS101 Section: S1 Bid (e$): 50 | Change to bidding round 1. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field, section into section input field and bid amount into bid(e$) input field. Submit. | Bid unsuccessful. Error message shown.
9 | 024-drop_bid | Validate that student with correct course code and section can drop bid if bid exists in the system during active bidding round | Home Page Username: ben.ng.2009 Password: qwerty129 Drop Bid Page Course ID: IS100 Section: S1 | Change to bidding round 1. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field and section into section input field during active bidding round. Submit. | Drop bid successful.
10 | 025-drop_bid | Validate that student cannot drop bid during active bidding round if course code does not exist in the system's records | Home Page Username: ben.ng.2009 Password: qwerty129 Drop Bid Page Course ID: IS110 Section: S1 | Change to bidding round 1. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field and section into section input field during active bidding round. Submit. | Drop bid unsuccessful. Error message shown.
11 | 026-drop_bid | Validate that student cannot drop bid during active bidding round if course is valid but section does not exist in the system's records | Home Page Username: ben.ng.2009 Password: qwerty129 Drop Bid Page Course ID: IS100 Section: S9 | Change to bidding round 1. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field and section into section input field during active bidding round. Submit. | Drop bid unsuccessful. Error message shown.
12 | 027-drop_bid | Validate that student cannot drop bid if current bidding round has already ended | Home Page Username: ben.ng.2009 Password: qwerty129 Drop Bid Page Course ID: IS100 Section: S1 | Change to bidding round 1. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field and section into section input field during active bidding round. Submit. | Drop bid unsuccessful. Error message shown.
13 | 028-drop_bid | Validate that student cannot drop bid if it is an active bidding round, course and section are valid but no such bid exists in the system's records | Home Page Username: ben.ng.2009 Password: qwerty129 Drop Bid Page Course ID: IS100 Section: S2 | Change to bidding round 1. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field and section into section input field during active bidding round. Submit. | Drop bid unsuccessful. Error message shown. |  |  | still need this? based on above one.
14 | 029-drop_section | Validate that student with correct course code and section can drop section if already enrolled in course and section during active bidding round | Home Page Username: zac.ng.2009 Password: qwerty153 Drop Section Page Course ID: IS100 Section: S1 | Change to bidding round 1. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field and section into section input field during active bidding round. Submit. | Drop bid successful. User is redirected back to page with success message shown. |  |  | Need to recheck the details of student
15 | 030-drop_section | Validate that student cannot drop section if already enrolled in course and section but course code is incorrect | Home Page Username: zac.ng.2009 Password: qwerty153 Drop Section Page Course ID: IS101 Section: S1 | Change to bidding round 1. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field and section into section input field during active bidding round. Submit. | Drop bid unsuccessful. Error message shown.
16 | 030-drop_section | Validate that student cannot drop section if already enrolled in course and section but section is incorrect | Home Page Username: zac.ng.2009 Password: qwerty153 Drop Section Page Course ID: IS100 Section: S1 | Change to bidding round 1. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field and section into section input field during active bidding round. Submit. | Drop bid unsuccessful. Error message shown.
17 | 031-drop_section | Validate that student cannot drop bid if current bidding round has already ended | Home Page Username: zac.ng.2009 Password: qwerty153 Drop Section Page Course ID: IS100 Section: S1 | Change to bidding round 1. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field and section into section input field during active bidding round. Submit. | Drop bid unsuccessful. Error message shown.
18 | 032-drop_section | Validate that student cannot drop bid if it is an active bidding round, courseand section are valid but no such bid exists in the system's records | Home Page Username: zac.ng.2009 Password: qwerty153 Drop Section Page Course ID: IS100 Section: S1 | Change to bidding round 1. Put username into username input field and password into password input field. Submit. Put course ID into course ID input field and section into section input field during active bidding round. Submit. | Drop bid unsuccessful. Error message shown.

## Iter2-JSON-PlceBidDrpBidSect
S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Actual Results | Pass/Fail
1 | Delete Bid | Validate that Admin can delete bid if it is an active round, userid, course, section are correct and bid exists in the system. | userid=ben.ng.2009 course=IS100 section=S1 token=eyJ0eXAiOiJKV1QiLCJhbGciOiJIUzI1NiJ9.eyJ1c2VybmFtZSI6ImFkbWluIiwiZGF0ZXRpbWUiOiIyMDE5LTEwLTA5IDAzOjE4OjM2In0.5lQBoMJcxCezkcvjTkHfiN2ZvYi1tIY4HhXTtB2FV-Q | Send the details through Request. Use the token to drop a student's bid for them. | { "status": "success" } |  |  | Note: all these are from the admin's side: to drop bids using tokens | Authenticate http://18.191.224.119/app/json/authenticate?r={ "userid": "admin", "password": "" } Drop Bid http://18.191.224.119/app/json/delete-bid?r={ "userid": "ben.ng.2009", "course": "IS100", "section": "S1" }&token=[tokenValue]
2 | Delete Bid | Validate that student cannot drop bid if course code does not exist in the system's records | userid=ben.ng.2009 course=IS110 section=S1 | Send the details through Request. Use the token to drop a student's bid for them. | { "status": "error", "message": [ "invalid course" ] } |  |  | Note: all these are from the admin's side: to drop bids using tokens | http://18.191.224.119/app/json-delete-bid?r={ "userid": "ben.ng.2009", "course": "IS110", "section": "S1" }&token=[tokenValue]
3 | Delete Bid | Validate that student cannot drop bid if userid does not exist in the system's records | userid=ben.tan.2009 course=IS100 section=S1 | Send the details through Request. Use the token to drop a student's bid for them. | { "status": "error", "message": [ "invalid userid" ] } |  |  | ADMIN
4 | Delete Bid | Validate that student cannot drop bid if course is valid but section does not exist in the system's records | userid=ben.tan.2009 course=IS100 section=S9 | Send the details through Request. Use the token to drop a student's bid for them. | { "status": "error", "message": [ "invalid section" ] } |  |  | ADMIN
5 | Delete Bid | Validate that student cannot drop bid if current bidding round has already ended | userid=ben.tan.2009 course=IS100 section=S1 | Send the details through Request. Use the token to drop a student's bid for them. | { "status": "error", "message": [ "round ended" ] } |  |  | ADMIN
6 | Delete Bid | Validate that student cannot drop bid if it is an active bidding round, course, userid and section are valid but no such bid exists in the system's records | userid=amy.tan.2009 course=IS100 section=S1 | Send the details through Request. Use the token to drop a student's bid for them. | { "status": "error", "message": [ "no such bid" ] } |  |  | ADMIN
| Drop Section | Validate that admin can drop a user's enrolment in a section during an active round if the course code, userid and section are correct. | userid=amy.tan.2009 course=IS100 section=S1 | Send the details through Request. Use the token to drop a student's bid for them. | { "status": "success" }
| Drop Section | Validate that admin cannot drop a user's enrolment in a section during an active round if the user is not enrolled. | userid=amy.tan.2009 course=MGMT001 section=S1 | Send the details through Request. Use the token to drop a student's bid for them. | { "status": "error", "message": [ "no such enrollment record" ] }
| Drop Section | Validate that admin cannot drop a user's enrolment in a section during an active round if the course code does not exist in the system's records. | userid=amy.tan.2009 course=IS110 section=S1 | Send the details through Request. Use the token to drop a student's bid for them. | { "status": "error", "message": [ "invalid course" ] }
| Drop Section | Validate that admin cannot drop a user's enrolment in a section during an active round if the userid does not exist in the system's records. | userid=alice.tan.2009 course=IS100 section=S1 | Send the details through Request. Use the token to drop a student's bid for them. | { "status": "error", "message": [ "invalid userid" ] }
| Drop Section | Validate that admin cannot drop a user's enrolment in a section during an active round if the course code exists in the system's records but the section id does not exist for the particular course. | userid=amy.tan.2009 course=IS100 section=S9 | Send the details through Request. Use the token to drop a student's bid for them. | { "status": "error", "message": [ "invalid section" ] }
| Drop Section | Validate that admin cannot drop a user's enrolment in a section if the course code, userid and section are correct but it is not an active round . | userid=amy.tan.2009 course=IS100 section=S1 | Change the round status to inactive. Send the details through Request. Use the token to drop a student's bid for them. | { "status": "error", "message": [ "round not active" ] }
| Update Bid | Validate that admin cannot add a bid for the student if the amount bidded is lower than the minimum bid for round 1. | userid=eddy.ng.2009 course=IS100 section=S1 e$=9 | Send the details through Request. Use the token to update a student's bid for them. | { "status": "error", "message": [ "bid too low" ] }
| Update Bid | Validate that admin cannot add a bid for the student if student does not have enough e-dollars to place the bid. | userid=eddy.ng.2009 course=IS100 section=S1 e$=9 | Send the details through Request. Use the token to update a student's bid for them. | { "status": "error", "message": [ "insufficient e$" ] }
| Update Bid | Validate that admin cannot add a bid for the student if the timeslot for the respective class clashes with that of a previously bidded section. | userid=eddy.ng.2009 course=IS100 section=S1 e$=10 | Send the details through Request. Use the token to update a student's bid for them. | { "status": "error", "message": [ "class timetable clash" ] }
| Update Bid | Validate that admin cannot add a bid for the student if the timeslot for the respective exam clashes with that of a previously bidded section. | userid=eddy.ng.2009 course=IS100 section=S1 e$=10 | Send the details through Request. Use the token to update a student's bid for them. | { "status": "error", "message": [ "exam timetable clash" ] }
| Update Bid | Validate that admin can update bid if userid, course code, section and amount is valid. However, it is an inactive round. | userid=eddy.ng.2009 course=IS100 section=S1 e$=10 | Send the details through Request. Use the token to update a student's bid for them. | { "status": "error", "message":["round ended"] }
| Update Bid | Validate that admin can update bid if userid, course code, section and amount is valid. However, student has completed the course already. | userid=eddy.ng.2009 course=IS100 section=S1 e$=10 | Send the details through Request. Use the token to update a student's bid for them. | { "status": "error", "message":["course completed"] }
| Update Bid | Validate that admin can update bid if userid, course code, section and amount is valid. However, student has already won a bid for a section in this course in a previous round. | userid=eddy.ng.2009 course=IS100 section=S1 e$=10 | Send the details through Request. Use the token to update a student's bid for them. | { "status": "error", "message":["course enrolled" ] }
| Update Bid | Validate that admin can update bid if userid, course code, section and amount is valid. However, student has already bidded for 5 sections. | userid=eddy.ng.2009 course=IS100 section=S1 e$=10 | Send the details through Request. Use the token to update a student's bid for them. | { "status": "error", "message":["section limit reached" ] }
| Update Bid | Validate that admin can update bid if userid, course code, section and amount is valid. However, student is in round 1 bidding and not able to bid for modules not from it's own school. | userid=eddy.ng.2009 course=IS100 section=S1 e$=10 | Send the details through Request. Use the token to update a student's bid for them. | { "status": "error", "message":["not own school course" ] }
| Update Bid | Validate that admin can update bid if userid, course code, section and amount is valid. However, there is 0 vacancy for the particular section. | userid=eddy.ng.2009 course=IS100 section=S1 e$=10 | Send the details through Request. Use the token to update a student's bid for them. | { "status": "error", "message":["no vacancy" ] }

## Iter 3-Manual-StartClearRound
S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Actual Results | Pass/Fail

## Iter 3-JSON-StartClearRound
S/N | Functionality (as per requirements document) | Description | Test Inputs | Test Procedure | Expected Results | Actual Results | Pass/Fail